## Sheet1
Updated June 9, 2022
Timeline for COE P&T process: 2022-2023
Deadlines |  | Promotion/Tenure | Midterm
Candidate hands off reviewed dossier to unit |  | 2022-06-24 | 2023-01-30
Unit hands off completed dossier to College |  | 2022-12-02 | 2023-04-07
College Committee hands off dossier and letter to Dean |  | 2023-01-20 | 2023-05-05
College hands off final dossier |  | 2023-02-10 | 2023-06-02
Provost notifies candidate of decision |  | June 2023 | NA
Component and task | Responsibility | Promotion/Tenure | Midterm
Initial dossier (candidate's portion)
Notify unit head of candidacy (if non-mandatory) | Candidate | April | NA
Preparation of candidate's portion of dossier | Candidate | May | November
Identify 8 suggested external reviewers | Candidate | June | NA
Identify 4-8 suggested student names for student evaluation letter | Candidate | June | December
Waiver of Access Decision Recorded | Candidate | June | December
Finalization of initial dossier | Candidate | June | 2023-01-30
Materials complete by |  | 2022-06-24 | 2023-01-30
Candidate Signs Section X of the Dossier that the open part of the dossier is complete (No dossier changes allowed after this date) | Candidate | 2022-09-30 | 2023-01-30
Candidate provides updates to Dossier only as an Addendum after Sep 30 or Jan 31 | Candidate | 12/2/2022 For COE-FSC | 4/7/2023 for COE-FSC
External reviews
Identify candidate reviewers | Unit administration | July | NA
Contact candidate reviewers requesting participation | Unit administration | July | NA
PD added to dossier | Unit administration | July
Send initial dossier to reviewers | Unit administration | July | NA
Collect external letters (with reminders or substitutes) | Unit administration | August | NA
Document the external review process in the dossier | Unit administration | August | NA
Materials complete by |  | 2022-09-09 | NA
Peer teaching evaluation
Collect previous peer teaching evaluations | Unit administration | June | December
Identify peer reviewers | Unit committee | Ongoing | Ongoing
Write peer evaluation letter | Peer subgroup | October | February
Materials complete by |  | 2022-10-14 | 2023-02-17
Student letters
Identify students and make arrangements with them | Unit administration | First week of classes | Mid-January
Collect individual student letters | Unit administration | 2nd week October | 2nd week February
Arrange for summary student letter | Unit administration | 2nd week October | 2nd week February
Collect summary student letter | Unit administration | 3rd week October | 3rd week February
Document the student letter process in the dossier | Unit administration | 3rd week October | 3rd week February
Materials complete by |  | 2022-10-14 | 2023-02-17
Unit committee
Contact candidate for updated dossier | Unit administration | 2022-09-02 | NA
Complete Form A for the dossier | Unit administration | 2022-09-09 | January
Assemble offer letter and add to dossier | Unit administration | 2022-09-09 | January
Candidate Signs Section X of the Dossier that the open part of the dossier is complete (No dossier changes allowed after this date) | Unit administration | 2022-09-30 | 2023-01-31
Meet as needed to discuss criteria | Unit committee | Early October | Early February
Document in the dossier the process used to form the committee and the voting process | Unit administration | Early October | Early February
Review materials | Unit committee | October-early November | February-early March
Submit committee letter | Unit committee | Mid November | Early/Mid-March
Materials complete by |  | 2022-11-11 | 2023-03-10
Unit head
Review materials | Unit head | Mid/Late November | Mid/Late March
Finalize unit head letter | Unit head | Mid/Late November | Mid/Late March
Meet with candidate ("H/C" meeting); candidate to review all evaluative letters, excluding external letters | Unit head | Mid/Late November | Mid/Late March
Materials complete by |  | Mid/Late November | Mid/Late March
Optional candidate rebuttal
Write letter as desired | Candidate | 7 days after H/C mtg | 7 days after H/C mtg
Materials complete by |  | 2022-12-02 | 2023-04-07
Assembly of unit-level dossier
Assemble materials from external, peer, student and unit reviews | Unit administration | As items are complete | As items are complete
Finalize and submit to COE (no rebuttal) | Unit adminstration | After H/C meeting | After H/C meeting
Materials complete by |  | Late November | Late March
Finalize and submit to COE (with rebuttal) | Unit administration | As soon as complete | As soon as complete
Materials complete by |  | 2022-12-02 | 2023-04-07
COE Faculty Status Committee
Meet as needed to discuss process | COE committee | Fall term | n/a
Review materials | COE committee | Mid Dec to mid Jan | Mid April to 1st week of May
Submit letter | COE committee | 3rd week January | 1st week of May
Materials complete by |  | 2023-01-20 | 2023-05-05
Dean
Review materials | Dean | Late Jan to early Feb | mid-May
Finalize Dean's letter | Dean | early February | mid-May
Meet with candidate ("D/C" meeting) and review COE committee and dean's letter | Dean | 2nd week February | late May
Materials complete by |  | 2023-02-10 | 2023-06-02
Optional candidate rebuttal
Write letter if desired | Candidate | 7 days after D/C meeting | 7 days after D/C meeting
Materials complete by |  | 2023-02-17 | 2023-06-09
Assembly of college-level dossier
Assemble materials | COE Administration | Mid February | NA
Finalize and hand off | COE Administration | Mid February | NA
Materials complete by |  | Mid February | NA
Committee membership | Responsibility | Deadline
Unit voting: replacemement of COE FSC members rotating off | Unit administration | 2023-04-28